## DASHBOARD
AEROSOL PLANT · INSTALLATION DASHBOARD
Last Updated | 2026-05-21
Total Tasks | Completed | In Progress | Not Started | Blocked
129 | 44 | 37 | 40 | 4
MACHINE SECTIONS
Machine (tap to view tasks) | ⚡ Elec. Pending | ⚙ Mech. Pending | Total Pending | ✓ Done
Press | 1 | 14 | 15 | 14
Trimming | 1 | 2 | 3 | 6
Washing | 3 | 13 | 16 | 2
Lacquer | 2 | 2 | 4 | 7
Base Coat | 0 | 1 | 1 | 3
Printing | 3 | 7 | 10 | 2
Over Varnish | 0 | 1 | 1 | 4
Main Oven | 0 | 0 | 0 | 3
Necking | 1 | 4 | 5 | 1
Mixer | 1 | 0 | 1 | 1
General | 10 | 19 | 29 | 1
PENDING BY PRIORITY
High Priority |  |  | 49
Medium Priority |  |  | 26
Low Priority |  |  | 10
STATUS REFERENCE
In Progress | Not Started | Blocked | Completed | Pending Procurement

## TRACKER
AEROSOL PLANT · INSTALLATION TRACKER | [7 empty] | ← Dashboard
# | Machine | Category | Task Description | Priority | Progress | Status | Remarks | Updated
1 | Press | Electrical | Close all electrical panels and cable trays | High | 10% | In Progress
2 | Press | Electrical | SOV pneumatic press clutch service | – | 100% | Completed
3 | Press | Electrical | Hopper motor installation and testing (Dry Run) | – | 100% | Completed
4 | Press | Electrical | Hopper Motor installation | – | 100% | Completed
5 | Press | Electrical | Cable trays installation | – | 100% | Completed
6 | Press | Mechanical | Slug Feeding Hopper with switch — complete unit | High | 50% | In Progress
7 | Press | Mechanical | Gear Oil Lubrication pumping system setup | High | 40% | In Progress | Pump sent for repairing
8 | Press | Mechanical | Welding & fixing gear oil tank brackets and sheet | Medium | 40% | In Progress
9 | Press | Mechanical | Press machine auto lubrication — pending tasks | High | 30% | In Progress | Procurement in process
10 | Press | Mechanical | Tools for press machine — urgent procurement | High | 20% | In Progress | In progress
11 | Press | Mechanical | 02 Dust collection pipes to be installed | Medium | 0% | Not Started
12 | Press | Mechanical | Dust Collection blower — connection with piping | Medium | 0% | Not Started | Blower to be procured
13 | Press | Mechanical | Fix lubrication tray with slope for drainage | Medium | 0% | Not Started
14 | Press | Mechanical | Oil collection tank — place directly under tray | Medium | 0% | Not Started
15 | Press | Mechanical | Operator Platform (incomplete stand) to be made | Low | 0% | Not Started
16 | Press | Mechanical | Damping rubber pads over slug feeding tray | Low | 0% | Not Started
17 | Press | Mechanical | Scoop (chamach) required for slug handling | Low | 0% | Not Started | Khalid sb
18 | Press | Mechanical | Baling machine check from local vendor | Low | 0% | Not Started | Khalid sb
19 | Press | Mechanical | Press machine auto running on slug | High | 0% | Not Started | Awaiting pending task completion
20 | Press | Mechanical | Auto gripper fitting / checking | – | 100% | Completed
21 | Press | Mechanical | Slug Holder channel | – | 100% | Completed
22 | Press | Mechanical | Press main slide installation | – | 100% | Completed
23 | Press | Mechanical | Press conveyor fixation | – | 100% | Completed
24 | Press | Mechanical | Oil pump motor repairing | – | 100% | Completed
25 | Press | Mechanical | Press & Trimming compressor line fixed | – | 100% | Completed
26 | Press | Mechanical | Press Clutch NRV repaired | – | 100% | Completed
27 | Press | Mechanical | Oil pump replacing and troubleshooting | – | 100% | Completed
28 | Press | Mechanical | Press timing and alignment with testing | – | 100% | Completed
29 | Press | Mechanical | Die & punch stroke setting | – | 100% | Completed
30 | Trimming | Electrical | Scrap collector wiring and troubleshooting | High | 90% | In Progress | Magnetic switch faulty — to be changed
31 | Trimming | Electrical | Electrical Panel checked / Tested | – | 100% | Completed
32 | Trimming | Electrical | Startup main motor | – | 100% | Completed
33 | Trimming | Electrical | Pneumatic and Electrical operation check | – | 100% | Completed
34 | Trimming | Mechanical | Oiling / greasing / parts replacement / testing | High | 80% | In Progress | Oil pump maintenance pending
35 | Trimming | Mechanical | Trimming machine dry run | High | 0% | Blocked | Dry run awaiting — cutter blade sent for sharpening
36 | Trimming | Mechanical | Trimming startup | – | 100% | Completed
37 | Trimming | Mechanical | Conveyor alignment — Trimming to Washing | – | 100% | Completed
38 | Trimming | Mechanical | Conveyor — Press to Trimming input | – | 100% | Completed
39 | Washing | Electrical | Heaters to be checked and replaced if required | High | 30% | In Progress | After press & trimming startup
40 | Washing | Electrical | Disconnect wiring before washing the machine | High | 0% | In Progress | Khalid sb
41 | Washing | Electrical | Ensure all exhaust fans on floor are operational | High | 0% | In Progress | Cable & connection required — UTI team
42 | Washing | Mechanical | Chain Repairing | High | 0% | In Progress | Sent to Karachi for repairing
43 | Washing | Mechanical | Process identification, missing parts, inspection | High | 0% | In Progress | In collaboration with Lindsay
44 | Washing | Mechanical | Rinsing Recycling Tank — decoating & cleaning | High | 50% | In Progress
45 | Washing | Mechanical | Spraying Jets Section — cleaning / scraping | High | 50% | In Progress
46 | Washing | Mechanical | Washing machine chain — repair and reinstallation check | High | 30% | In Progress | Repairing in progress in Karachi — to be checked after installation
47 | Washing | Mechanical | Washing machine piping and blower installation | High | 20% | In Progress | To be checked with Lindsay — blower available for installation
48 | Washing | Mechanical | Separate storage tanks (detergent / cold / hot water) | High | 0% | Not Started | Khalid sb
49 | Washing | Mechanical | Washing rinse recycling tank (rusty) — clean | High | 0% | Not Started | Khalid sb
50 | Washing | Mechanical | Heat exchanger for washing system — procure & install | High | 0% | Not Started | Khalid sb
51 | Washing | Mechanical | Washing process flow — review and implement | High | 0% | Not Started | Khalid sb
52 | Washing | Mechanical | Washing unit tanks — sizes and quantities for quotation | High | 0% | Not Started | Sizes & quantities to be provided for quotation
53 | Washing | Mechanical | Washing unit drain plan — flexible pipes after tank installation | Medium | 0% | Not Started | To be installed after tank installation
54 | Washing | Mechanical | Inspect all rubber pipes — replace if damaged | High | 0% | Blocked | After chain arrival — Khalid sb
55 | Washing | Mechanical | All gears greasing | – | 100% | Completed
56 | Washing | Mechanical | Gears alignment | – | 100% | Completed
57 | Lacquer | Electrical | All heaters — check, fix or replace faulty | High | 90% | In Progress | 2 faulty heaters need replacement
58 | Lacquer | Electrical | Air filter to be installed before lacquer line | High | 0% | Not Started | Khalid sb
59 | Lacquer | Electrical | Blower main motor connection and testing | – | 100% | Completed
60 | Lacquer | Mechanical | Cans Holders — dismantled, clean with thinner | Medium | 50% | In Progress
61 | Lacquer | Mechanical | Small dedicated air tank / receiver for lacquer | Medium | 0% | Not Started | Khalid sb
62 | Lacquer | Mechanical | Spray Guns — cleaned with thinner | – | 100% | Completed
63 | Lacquer | Mechanical | Spray Mount Drum — scraped & cleaned | – | 100% | Completed
64 | Lacquer | Mechanical | Mandrel Plate — scraped & cleaned | – | 100% | Completed
65 | Lacquer | Mechanical | Exhaust Sieve — cleaned | – | 100% | Completed
66 | Lacquer | Mechanical | Frame Body — cleaned | – | 100% | Completed
67 | Lacquer | Mechanical | Oven Chain cleaning | – | 100% | Completed
68 | Base Coat | Mechanical | Rollers — dismantled, to be chrome plated | Medium | 50% | In Progress | Sent for chrome plating
69 | Base Coat | Mechanical | Rollers Housing — cleaned and greased | – | 100% | Completed
70 | Base Coat | Mechanical | Mandrels — cleaned | – | 100% | Completed
71 | Base Coat | Mechanical | Frame Body — cleaned | – | 100% | Completed
72 | Printing | Electrical | Servo motor troubleshooting | High | 0% | Not Started
73 | Printing | Electrical | White LED lighting for printing and oven area | Medium | 0% | Not Started | Khalid sb
74 | Printing | Electrical | Final printing plan and PLC delivery & inspection | High | 20% | Pending Procurement | PLC and supporting items to be delivered and inspected — Material in transit
75 | Printing | Electrical | CTC cleaning of machine panels interface | – | 100% | Completed
76 | Printing | Electrical | PLC installation | – | 100% | Completed
77 | Printing | Mechanical | All printing rollers — dismantle, clean, buff, chrome plate | High | 60% | In Progress
78 | Printing | Mechanical | Rollers (Tubex team) — ready for chrome plating | High | 70% | In Progress
79 | Printing | Mechanical | Bearings — cleaning & greasing | Medium | 50% | In Progress
80 | Printing | Mechanical | Ink Fountain — cleaning | Medium | 50% | In Progress
81 | Printing | Mechanical | Roller Train Frame — cleaning | Medium | 50% | In Progress
82 | Printing | Mechanical | Printing machine rollers — deep clean, rubber & chrome inspection | High | 40% | In Progress | Deep cleaning in progress; rubber roller quotation taken; chrome coating to be checked after inspection
83 | Printing | Mechanical | Aluminium oil tank — fabricate & install | Medium | 0% | Not Started | Khalid sb
84 | Over Varnish | Electrical | Motors checking and troubleshooting | – | 100% | Completed
85 | Over Varnish | Mechanical | Rollers — dismantled, to be chrome plated | Medium | 50% | In Progress | Sent for chrome plating
86 | Over Varnish | Mechanical | Mandrels — cleaned | – | 100% | Completed
87 | Over Varnish | Mechanical | Rollers Housing — cleaned and greased | – | 100% | Completed
88 | Over Varnish | Mechanical | Frame Body — cleaned | – | 100% | Completed
89 | Main Oven | Electrical | Cable trays installation | – | 100% | Completed
90 | Main Oven | Electrical | Blower motor connection and testing | – | 100% | Completed
91 | Main Oven | Mechanical | Motors alignment w.r.t marking | – | 100% | Completed
92 | Necking | Electrical | Necking machine — electrical supply troubleshooting for dry run | High | 20% | In Progress | Interlocking will be redesigned and checked
93 | Necking | Electrical | Electrical troubleshooting and testing | – | 100% | Completed
94 | Necking | Mechanical | Cans Grippers / Holders — cleaning | Medium | 50% | In Progress | Tubex team
95 | Necking | Mechanical | Two sets of press dies, springs & nut bolts required | High | 0% | Not Started | Khalid sb
96 | Necking | Mechanical | Buffing and polishing on necking machine tools | Medium | 0% | Not Started | Khalid sb
97 | Necking | Mechanical | Kluber oil & grease for necking machine | Medium | 0% | Not Started | Khalid sb
98 | Mixer | Electrical | Mixer installation and automation — auto feeding flow design | Medium | 0% | Pending Procurement | Flow to be designed for auto feeding on press — quotation awaiting for conveyor
99 | Mixer | Electrical | Main motor testing | – | 100% | Completed
100 | General | Electrical | Ensure all electrical circuits & cable trays closed | High | 0% | In Progress | After each section completion — Khalid sb
101 | General | Electrical | Transformer load increase to 625 kW — utility application | High | 30% | In Progress | Application in process
102 | General | Electrical | Testing of Control Logics & Circuits | High | 0% | Not Started | Target: 05-Apr-2026
103 | General | Electrical | Termination of cables & wires — Pre-commissioning | High | 0% | Not Started | Target: 15-Apr-2026
104 | General | Electrical | Verify electrical panels, control wiring, interlocks | High | 0% | Not Started | Target: 10-May-2026
105 | General | Electrical | Identify faulty machines / panels for rectification | High | 0% | Not Started | Target: 15-May-2026
106 | General | Electrical | Verify electrical panels, wiring & interlocks — Press to Washing | High | 0% | Blocked | Pending until Washing Machine electrical work is completed
107 | General | Electrical | Verify electrical panels, wiring & interlocks — Washing to Necking | High | 0% | Blocked | After material procurement; electrical revamping team to be deputed
108 | General | Electrical | Main Power Cable Termination & Execution Plan | High | 0% | Pending Procurement | Wires and auxiliaries to be ordered against BOQ
109 | General | Electrical | Electrical panels for power distribution — procurement review | High | 0% | Pending Procurement | New panels arranged; feedback needed on further procurement items
110 | General | Mechanical | Main header & distribution line to all sections | High | 95% | In Progress
111 | General | Mechanical | Ensure proper cleaning of entire machine | High | 0% | In Progress | Khalid sb
112 | General | Mechanical | Full unit inspection with Mr. Babar's team | High | 0% | In Progress | Khalid sb
113 | General | Mechanical | Compressor piping — dryer and auto drain system | High | 50% | In Progress | Mechanical and electrical installation in process
114 | General | Mechanical | Machine Operating Manuals — arrange from OEM | Medium | 10% | In Progress | Required in Russian and German language
115 | General | Mechanical | Daily coordination & reporting mechanism | Low | 0% | In Progress | As per the plan
116 | General | Mechanical | Check motors, conveyors, spindles, ovens, actuators | High | 0% | Not Started
117 | General | Mechanical | Test each machine individually without load | High | 0% | Not Started
118 | General | Mechanical | Overall machine paint | Medium | 0% | Not Started
119 | General | Mechanical | Modify exhaust duct pipes — prevent rainwater entry | Medium | 0% | Not Started | Awaiting quotation — Khalid sb
120 | General | Mechanical | Check & install lubrication drum foundation | Medium | 0% | Not Started | On startup — Khalid sb
121 | General | Mechanical | Make stands for all spare rolls | Low | 0% | Not Started | Awaiting quotation — Khalid sb
122 | General | Mechanical | Full operator toolset & tool trolley system | Medium | 0% | Not Started | Khalid sb
123 | General | Mechanical | Lab equipment to be sourced | Medium | 0% | Not Started | Khalid sb
124 | General | Mechanical | Filter plant — fix for drinking water | Low | 0% | Not Started | Khalid sb
125 | General | Mechanical | Dust bins for office areas | Low | 0% | Not Started | Khalid sb
126 | General | Mechanical | Big cartons for temporary storage of cans | Low | 0% | Not Started | Khalid sb
127 | General | Mechanical | Boxes / Bins for cans packing (Alpha Container) | Low | 0% | Not Started | Khalid sb
128 | General | Mechanical | Mr. Lindsay next visit — finalize commissioning dates | Medium | 0% | Not Started | Final commissioning visit dates to be finalized upon startup
129 | General | Mechanical | Dismantle all rollers for inspection | – | 100% | Completed | Done — Khalid sb

## HOW TO UPDATE
HOW TO UPDATE — QUICK GUIDE
COLUMN / STEP | INSTRUCTION
COLUMN | WHAT TO DO
Machine | Click the cell — a dropdown appears. Pick the machine name.
Category | Pick Electrical or Mechanical from the dropdown.
Task Description | Type the task clearly and briefly.
Priority | High = urgent / blocking. Medium = important. Low = when possible.
Progress | Type a number: 0 = not started, 50 = halfway done, 100 = complete.
Status | Pick from dropdown: Not Started / In Progress / Completed / Blocked / Pending Procurement.
Remarks | Short notes — vendor, reason for delay, Khalid sb instruction, etc.
Updated | Type today's date when you update any row.
Add a new task | Scroll to the bottom. Type in the next empty row. All dropdowns work there too.
Filter by machine | Click the filter arrow (▼) on the Machine column. Tick only the machine you want.
Hide completed | Click the filter arrow on Status. Untick Completed. Click OK.
Dashboard links | On the Dashboard, click any machine name (underlined blue) to jump straight to it.
Back to Dashboard | In the Tracker, click '← Dashboard' in the top-right corner of the sheet.