## DASHBOARD
AEROSOL PLANT · Installation & Commissioning Tracker
Last Updated | 2026-06-19
Overall % | Total Tasks | Completed | In Progress | Not Started | Hold | Pending Procurement
43.97% | 166 | 57 | 40 | 62 | 0 | 6
MACHINE SECTIONS
Machine | Elec. Pending | Mech. Pending | Other Pending | Total Pending | Completed | Overall %
⚙️ Tumbler | 1 | 2 | 0 | 3 | 2 | 46%
⚙️ Press | 1 | 4 | 0 | 5 | 14 | 80%
✂️ Trimming | 2 | 8 | 0 | 10 | 7 | 51.18%
💧 Washing | 3 | 13 | 0 | 16 | 3 | 22.11%
🎨 Lacquer | 0 | 1 | 0 | 1 | 11 | 93.33%
🔄 Accumulator | 0 | 1 | 0 | 1 | 0 | 50%
🖌️ Base Coat | 2 | 6 | 0 | 8 | 2 | 34.5%
🖨️ Printing | 4 | 5 | 1 | 10 | 4 | 52.5%
✨ Over Varnish | 3 | 4 | 1 | 8 | 4 | 42.92%
🔥 decoration Oven | 2 | 0 | 1 | 3 | 2 | 40%
🔩 Necking | 1 | 7 | 1 | 9 | 3 | 30.83%
📦 Auto strapping machine | 1 | 2 | 0 | 3 | 0 | 0%
📦 Manual strapping machine | 1 | 1 | 0 | 2 | 0 | 0%
💨 Compressor | 0 | 2 | 0 | 2 | 3 | 60%
📋 General | 3 | 5 | 8 | 16 | 2 | 23.33%
PENDING BY PRIORITY
High Priority |  |  |  | 66
Medium Priority |  |  |  | 39
Low Priority |  |  |  | 3
STATUS REFERENCE
In Progress | Not Started | Blocked | Completed | Pending Procurement

## TRACKER
AEROSOL PLANT · INSTALLATION TRACKER | [8 empty] | ← Dashboard
# | Machine | Category | Task Description | Priority | Progress | Status | Responsible | Deadline | Remarks
1 | Accumulator | Electrical | Dry run | High | 80% | In Progress | Arsalan |  | on machine testing
2 | Accumulator | Mechanical | chain & bearing greasing | Medium | 100% | Completed | Arsalan
3 | Accumulator | Mechanical | Tension Cylinders to check and replace | Medium | 10% | In Progress | Arsalan
4 | Auto Strapping Machine | Mechanical | to place and install at designated location | Medium | 0% | Not Started | Arsalan
5 | Auto Strapping Machine | Mechanical | Dry run | Low | 0% | Not Started | Arsalan
6 | Auto Strapping Machine | Electrical | wiring and connections to be done | Medium | 0% | Not Started | Arsalan
7 | Base Coat | Mechanical | Fumes collector piping to install | Medium | 0% | Not Started | Saqib | 2026-06-19 19:00
8 | Base Coat | Mechanical | Rollers Housing — cleaned and greased | Medium | 100% | Completed | Saqib | 2026-06-24 19:00
9 | Base Coat | Mechanical | Mandrels — cleaned | Medium | 100% | Completed | Saqib | 2026-06-24 19:00
10 | Base Coat | Mechanical | Frame Body — cleaned | Medium | 100% | Completed | Saqib | 2026-06-24 19:00
11 | Base Coat | Mechanical | Spare Rubberize rollers | High | 50% | In Progress | Saqib | 2026-06-24 19:00
12 | Base Coat | Mechanical | Air regulator pneumatic fitting to check and rectify and fixation | Medium | 100% | Completed | Arsalan | 2026-06-24 19:00
13 | Base Coat | Mechanical | driving gear chain box enclosure at back | Medium | 100% | Completed | Arsalan | 2026-06-24 19:00
14 | Base Coat | Electrical | closure of all cable trays/ panels | Medium | 40% | In Progress | Arsalan | 2026-06-24 19:00
15 | Base Coat | Mechanical | Rawal bolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-24 19:00
16 | Base Coat | Electrical | PLC installation & termination | High | 100% | Completed | Arsalan | 2026-06-24 19:00
17 | Compressor | Electrical | Compressor dryer and auto drain electrical connection | High | 100% | Completed | Arsalan
18 | Compressor | Mechanical | Compressor piping — dryer and auto drain system | High | 100% | Completed | Arsalan
19 | Compressor | Mechanical | main pipe to be elevated downward for smooth drainage | Medium | 0% | Not Started | Arsalan
20 | Compressor | Mechanical | individual section pipes/ branches to be supported/fixed/welded | Medium | 0% | Not Started | Arsalan
21 | Compressor | Electrical | dryer wiring and connection to be done. | High | 100% | Completed | Arsalan
22 | Decoration Oven | Electrical | Heaters to be checked and replaced if required | High | 80% | In Progress | Arsalan |  | sample needed for ordering
23 | Decoration Oven | Electrical | Blower motor connection and testing | High | 100% | Completed | Arsalan
24 | Decoration Oven | Electrical | temperature gauges to be checked & installed | High | 70% | In Progress | Arsalan
25 | Decoration Oven | Mechanical | Oven Dry run | High | 0% | Not Started | Arsalan |  | Cleaning in progress & Heater testing in progress
26 | Decoration Oven | Mechanical | Motors alignment w.r.t marking | High | 100% | Completed | Arsalan |  | Khalid Shb observations
27 | FG Conveyor | Mechanical | Realignment of conveyor to be done as per Lindsay recommendation | Medium | 100% | Completed | Arsalan
28 | FG Conveyor | Electrical | connection/wiring to be done | Medium | 0% | Not Started | Arsalan
29 | General | General | Machine Operating Manuals | Medium | 10% | In Progress | Saqib
30 | General | General | Overall machine paint | Medium | 10% | In Progress | Saqib
31 | General | Mechanical | Modify exhaust duct pipes — prevent rainwater entry bends installation | Medium | 100% | Completed | Saqib
32 | General | Mechanical | Test each machine individually without load | Medium | 80% | In Progress | Arsalan
33 | General | General | Ensure proper cleaning of entire machine | Medium | 80% | In Progress | Saqib
34 | General | Mechanical | Scoop required for slug handling | Medium | 100% | Completed | Saqib
35 | General | Mechanical | Baling machine procurement | Medium | 0% | Pending Procurement | Saqib
36 | General | Mechanical | scrap collector container to be made/procured for trimming | Medium | 0% | Not Started | Saqib
37 | General | Electrical | White LED lighting for printing and oven area | Medium | 0% | Not Started | Saqib
38 | General | General | Make stands for all spare rolls | Medium | 10% | In Progress | Saqib
39 | General | General | Full operator toolset & tool trolley system | Medium | 100% | Completed | Saqib
40 | General | General | Lab equipment to be sourced | Medium | 0% | Pending Procurement | Saqib
41 | General | General | Dust bins for office areas | Medium | 100% | Completed | Saqib
42 | General | General | Big cartons for temporary storage of cans | Medium | 100% | Completed | Saqib
43 | General | Electrical | Transformer load increase to 625 kW — utility application | High | 0% | Not Started | Saqib |  | Application in process
44 | General | Electrical | Ensure all exhaust fans on floor are operational | High | 90% | In Progress | Saqib |  | partially operational
45 | General | Mechanical | Operator's Platform | Medium | 100% | Completed | Saqib |  | new to be ordered
46 | Lacquer | Electrical | All heaters — check, fix or replace faulty | High | 100% | Completed | Arsalan | 2026-05-14 19:00
47 | Lacquer | Electrical | Blower main motor connection and testing | High | 100% | Completed | Arsalan | 2026-06-09 19:00
48 | Lacquer | Mechanical | Spray Guns — cleaned with thinner | High | 100% | Completed | Saqib | 2026-06-09 19:00
49 | Lacquer | Mechanical | Spray Mount Drum — scraped & cleaned | High | 100% | Completed | Saqib | 2026-06-09 19:00
50 | Lacquer | Mechanical | Mandrel Plate — scraped & cleaned | Medium | 100% | Completed | Saqib | 2026-06-09 19:00
51 | Lacquer | Mechanical | Exhaust Sieve — cleaned | Medium | 100% | Completed | Saqib | 2026-06-09 19:00
52 | Lacquer | Mechanical | Dry run | Medium | 100% | Completed | Arsalan | 2026-06-09 19:00
53 | Lacquer | Mechanical | Frame Body — cleaned | Medium | 100% | Completed | Saqib | 2026-06-09 19:00
54 | Lacquer | Mechanical | Oven Chain cleaning | Medium | 100% | Completed | Saqib | 2026-06-09 19:00
55 | Lacquer | Mechanical | Internal Lacquering Dry run | High | 100% | Completed | Arsalan | 2026-06-14 19:00
56 | Lacquer | Mechanical | lacquer Storage vessel installation with pneumatic fittings | Medium | 100% | Completed | Saqib | 2026-06-14 19:00
57 | Lacquer | Mechanical | fixing can holders after cleaning | Medium | 100% | Completed | Arsalan | 2026-06-14 19:00
58 | Lacquer | Mechanical | Cans Holders — dismantled, clean with thinner | Medium | 100% | Completed | Saqib | 2026-06-14 19:00
59 | Lacquer | Mechanical | Cans In-feed conveyor chain rods to procure and install | Medium | 100% | Completed | Saqib | 2026-06-14 19:00
60 | Lacquer | Mechanical | Cans Grippers to be procured/fabricated | Medium | 100% | Completed | Saqib | 2026-06-14 19:00
61 | Lacquer | Electrical | Spray guns spray timings to be set | Medium | 100% | Completed | Arsalan | 2026-06-14 19:00
62 | Lacquer | Mechanical | Cans In-feed conveyor Inspection & testing | Medium | 100% | Completed | Arsalan | 2026-06-14 19:00
63 | Lacquer Oven | Mechanical | Oven Chain & bearing greasing | Medium | 80% | In Progress | Arsalan | 2026-06-14 19:00
64 | Lacquer Oven | Electrical | closure of electrical panels | Medium | 0% | Not Started | Arsalan | 2026-06-14 19:00
65 | Lacquer Oven | Mechanical | Oven back metallic cover sheet to place | Medium | 0% | Not Started | Arsalan | 2026-06-14 19:00
66 | Manual Strapping Machine | Mechanical | to place and install at designated location | Low | 0% | Not Started | Arsalan
67 | Manual Strapping Machine | Electrical | wiring and connections to be done | Low | 0% | Not Started | Arsalan
68 | Necking | Mechanical | Infeed tray installation from feeding unit to necking machine | Medium | 0% | Not Started | Arsalan
69 | Necking | Mechanical | PVC ejection pipe installation from necking for cans discharge | Medium | 0% | Not Started | Arsalan
70 | Necking | Mechanical | scrap collection tank to install from necking | Medium | 0% | Not Started | Arsalan
71 | Necking | Mechanical | Conveyor installation after ejection pipe | Medium | 0% | Not Started | Arsalan
72 | Necking | Mechanical | Necking machine Dry run | High | 50% | In Progress | Arsalan
73 | Necking | Electrical | Electrical troubleshooting and testing | High | 100% | Completed | Arsalan
74 | Necking | Mechanical | Cans Grippers / Holders — cleaning | Medium | 100% | Completed | Saqib
75 | Necking | Mechanical | Buffing and polishing on necking machine tools | Medium | 100% | Completed | Saqib
76 | Necking | Mechanical | Cans Grippers / Holders — deep cleaning (after dismantling) | Medium | 100% | Completed | Saqib
77 | Necking | Mechanical | Two sets of press dies, springs & nut bolts required | High | 0% | Not Started | Saqib
78 | Necking | Mechanical | Kluber oil & grease for necking machine | Medium | 0% | In Progress | Saqib
79 | Necking | Electrical | Necking machine — electrical supply troubleshooting for dry run | High | 60% | In Progress | Arsalan |  | Interlocking will be redesigned and checked
80 | Over Varnish | Mechanical | Rollers — dismantled, to be chrome plated | High | 100% | Completed | Saqib | 2026-06-14 19:00
81 | Over Varnish | Mechanical | Fumes collector piping to install | High | 0% | Not Started | Saqib | 2026-06-19 19:00
82 | Over Varnish | Mechanical | Spare Rubberize rollers | High | 50% | In Progress | Saqib | 2026-06-24 19:00
83 | Over Varnish | Electrical | closure of all cable trays/ panels | High | 30% | In Progress | Arsalan | 2026-06-24 19:00
84 | Over Varnish | Mechanical | Rawal bolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-24 19:00
85 | Over Varnish | Mechanical | varnish pump placement and installation with piping | High | 0% | Not Started | Arsalan | 2026-06-24 19:00
86 | Over Varnish | Mechanical | Printing Oven Dry run | High | 0% | Not Started | Arsalan | 2026-06-23 19:00
87 | Over Varnish | Electrical | Motors checking and troubleshooting | High | 50% | In Progress | Arsalan | 2026-06-24 19:00
88 | Over Varnish | Mechanical | Mandrels — cleaned | High | 100% | Completed | Saqib | 2026-06-24 19:00
89 | Over Varnish | Mechanical | Rollers Housing — cleaned and greased | High | 100% | Completed | Saqib | 2026-06-24 19:00
90 | Over Varnish | Mechanical | Frame Body — cleaned | High | 100% | Completed | Saqib | 2026-06-24 19:00
91 | Over Varnish | Electrical | PLC installation & termination | High | 100% | Completed | Arsalan | 2026-06-24 19:00
92 | Overall Machine Operation | Electrical | Main Power Cable Termination & Execution Plan | High | 0% | Not Started | Arsalan | 2026-06-12 19:00
93 | Overall Machine Operation | Electrical | Main Power Cable procurement | High | 60% | In Progress | Saqib
94 | Overall Machine Operation | Electrical | Electrical panels for power distribution | High | 20% | In Progress | Arsalan
95 | Overall Machine Operation | Electrical | Verify electrical panels, wiring & interlocks — Press to Washing | High | 50% | In Progress | Arsalan |  | Till Washing Machine electrical Work is completed
96 | Overall Machine Operation | Electrical | Testing of Control Logics & Circuits | High | 50% | In Progress | Arsalan
97 | Overall Machine Operation | Electrical | Verify electrical panels, wiring & interlocks — Washing to Necking | High | 50% | In Progress | Arsalan
98 | Press | Mechanical | Press & Trimming compressor temporary line fixed | High | 100% | Completed | Arsalan | 2026-05-15 19:00
99 | Press | Electrical | Close all electrical panels and cable trays | High | 20% | In Progress | Arsalan | 2026-06-15 19:00
100 | Press | Mechanical | Damping rubber pads over slug feeding tray | Low | 80% | In Progress | Saqib | 2026-06-15 19:00
101 | Press | Mechanical | Gear Oil Lubrication pumping system setup | High | 100% | Completed | Arsalan | 2026-06-15 19:00
102 | Press | Mechanical | Slug Feeding Hopper sheet to be fixed | High | 100% | Completed | Saqib | 2026-06-15 19:00
103 | Press | Mechanical | Tools for press machine | High | 90% | In Progress | Saqib | 2026-06-15 19:00
104 | Press | Electrical | Dust Collection blower installation | Medium | 100% | Completed | Arsalan | 2026-06-15 19:00
105 | Press | Electrical | SOV pneumatic press clutch service | High | 100% | Completed | Arsalan | 2026-06-14 19:00
106 | Press | Electrical | Hopper motor installation and testing | High | 100% | Completed | Arsalan | 2026-06-15 19:00
107 | Press | Electrical | Cable trays installation | High | 100% | Completed | Arsalan | 2026-06-15 19:00
108 | Press | Mechanical | Press Clutch NRV repaired | High | 100% | Completed | Arsalan | 2026-06-15 19:00
109 | Press | Mechanical | Press timing and alignment with testing | High | 100% | Completed | Arsalan | 2026-06-15 19:00
110 | Press | Mechanical | Die & punch stroke setting | High | 100% | Completed | Arsalan | 2026-06-15 19:00
111 | Press | Mechanical | Slug tray on/off switch to be installed | High | 100% | Completed | Saqib | 2026-06-15 19:00
112 | Press | Mechanical | Dust Collection blower piping | Medium | 100% | Completed | Saqib | 2026-06-15 19:00
113 | Press | Mechanical | Welding & fixing gear oil tank brackets and sheet | Medium | 100% | Completed | Arsalan | 2026-06-15 19:00
114 | Press | Mechanical | Fixing the lubrication tray properly with a slope for drainage | Medium | 100% | Completed | Arsalan | 2026-06-15 19:00
115 | Press | Mechanical | Place and install the Oil collection tank directly under the tray | Medium | 100% | Completed | Arsalan | 2026-06-15 19:00
116 | Press | Mechanical | Installation of Level sensor and Filter on the oil tank | Medium | 100% | Completed | Arsalan
117 | Press | Electrical | SOV coil pneumatic press clutch | High | 20% | In Progress | Saqib | 2026-06-15 19:00
118 | Press | Mechanical | Lubrication oil leakages to be rectified | Medium | 80% | In Progress | Arsalan
119 | Press | Mechanical | Tripping issue to be rectified | High | 10% | In Progress | Arsalan
120 | Press | Mechanical | compartment over feeder to fabricate | Medium | 10% | In Progress | saqib
121 | Press | Mechanical | Blower installation complete with piping and connections | Medium | 90% | In Progress | Arsalan
122 | Printing | Mechanical | Rollers — dismantled, to be chrome plated | High | 100% | Completed | Saqib | 2026-06-14 19:00
123 | Printing | Mechanical | Printing machine rollers — deep clean, rubber & chrome inspection | High | 100% | Completed | Saqib | 2026-06-14 19:00
124 | Printing | Electrical | solenoid coil for hydroulic | High | 100% | Completed | Saqib | 2026-06-14 19:00
125 | Printing | Mechanical | All printing rollers — dismantle, clean, buff, chrome plate | High | 100% | Completed | Saqib | 2026-06-14 19:00
126 | Printing | Electrical | CTC cleaning of machine panels interface | High | 80% | In Progress | Arsalan | 2026-06-13 19:00
127 | Printing | Electrical | PLC installation & termination | High | 100% | Completed | Arsalan | 2026-06-24 19:00
128 | Printing | Mechanical | Bearings — cleaning & greasing | High | 100% | Completed | Saqib | 2026-06-24 19:00
129 | Printing | Mechanical | Ink Fountain — cleaning | High | 100% | Completed | Saqib | 2026-06-24 19:00
130 | Printing | Mechanical | Roller Train Frame — cleaning | High | 100% | Completed | Saqib | 2026-06-24 19:00
131 | Printing | Mechanical | Dismantle all rollers for inspection & Cleaning | High | 100% | Completed | Saqib | 2026-06-24 19:00
132 | Printing | Electrical | Servo motor troubleshooting | High | 50% | In Progress | Arsalan | 2026-06-24 19:00
133 | Printing | Mechanical | Aluminum oil tank — fabricate & install | High | 100% | Completed | Saqib | 2026-01-01 19:00
134 | Printing | Electrical | closure of all cable trays/ panels | High | 0% | Not Started | Arsalan | 2026-06-24 19:00
135 | Printing | Mechanical | Rawlbolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-24 19:00
136 | Printing | Mechanical | Printing Machine Dry run | High | 50% | In Progress | Arsalan | 2026-06-24 19:00
137 | Printing | Mechanical | Main frame displacement to be fixed | High | 0% | In Progress | Arsalan
138 | Trimming | Mechanical | Installation of piping of Trimming Of blower | High | 100% | Completed | Arsalan | 2026-06-18 19:00
139 | Trimming | Mechanical | Conveyor alignment — Trimming to Washing | High | 50% | In Progress | Arsalan | 2026-06-18 19:00
140 | Trimming | Electrical | Trimming Scrap collector wiring and troubleshooting | High | 50% | In Progress | Arsalan | 2026-06-18 19:00
141 | Trimming | Electrical | Electrical Panel checked / Tested | High | 100% | Completed | Arsalan | 2026-06-18 19:00
142 | Trimming | Electrical | Startup main motor | High | 100% | Completed | Arsalan | 2026-06-18 19:00
143 | Trimming | Electrical | Pneumatic and Electrical operation check | High | 100% | Completed | Arsalan | 2026-06-18 19:00
144 | Trimming | Mechanical | Trimming startup | High | 100% | Completed | Arsalan | 2026-06-18 19:00
145 | Trimming | Mechanical | Conveyor — Press to Trimming input | High | 100% | Completed | Arsalan | 2026-06-18 19:00
146 | Trimming | Mechanical | Trimming machine dry run | High | 100% | Completed | Arsalan | 2026-06-18 19:00
147 | Trimming | Mechanical | closure of chain/gears/pneumatic assembly with box | High | 60% | In Progress | Arsalan | 2026-06-18 19:00
148 | Trimming | Electrical | closure of all cable trays/ panels | High | 0% | Not Started | Arsalan | 2026-06-18 19:00
149 | Trimming | Mechanical | pneumatic pressure valve for ejector pressure to install | High | 0% | Not Started | Arsalan | 2026-06-18 19:00
150 | Trimming | Mechanical | Installation of trimming blower | High | 100% | Completed | Arsalan | 2026-06-18 19:00
151 | Trimming | Mechanical | Fixing of Manual Oil Lubrication System | High | 100% | Completed | Saqib | 2026-06-18 19:00
152 | Trimming | Mechanical | Addition of closed cabinet for trim collection on machine side | High | 50% | Completed | Arsalan | 2026-06-18 19:00
153 | Trimming | Mechanical | Oiling / greasing / parts replacement / testing | High | 100% | Completed | Arsalan | 2026-06-18 19:00
154 | Tumbler | Electrical | Mixer installation and automation — auto feeding flow design | Medium | 0% | Pending Procurement | Arsalan |  | quotation awaiting for conveyor from Arsalan & Lindsay
155 | Tumbler | Mechanical | Slug Mixing Unit Dry run | Medium | 100% | Completed | Arsalan |  | Working on its auto feeding system
156 | Tumbler | Mechanical | Tumbler/Mixer wiring and connections to be done | High | 0% | Not Started | Arsalan
157 | Tumbler | Electrical | Main motor testing | High | 100% | Completed | Arsalan
158 | Tumbler | Mechanical | Tumbler/Mixer installation on platform | High | 100% | Completed | Arsalan
159 | Washing | Mechanical | chain installation | High | 100% | Completed | Arsalan | 2026-06-10 19:00
160 | Washing | Mechanical | Heat exchanger for washing system — procure & install | High | 0% | Not Started | Saqib | 2026-06-29 19:00
161 | Washing | Mechanical | Inspect all rubber pipes — replace if damaged | High | 0% | Not Started | Arsalan | 2026-06-29 19:00
162 | Washing | Mechanical | Washing unit tanks — sizes and quantities for quotation | Medium | 0% | In Progress | Saqib | 2026-06-14 19:00
163 | Washing | Electrical | Heaters to be checked and procured if required | High | 100% | Completed | Saqib | 2026-06-29 19:00
164 | Washing | Mechanical | Washing machine piping and blower installation | High | 90% | In Progress | Arsalan | 2026-06-29 19:00
165 | Washing | Mechanical | Washing unit drain flexible pipes after tank installation | High | 0% | Not Started | Arsalan | 2026-06-29 19:00
166 | Washing | Mechanical | Washing Machine Dry run | High | 0% | In Progress | Arsalan | 2026-06-29 19:00
167 | Washing | Electrical | Electrical Operating control panel to be relocated from trimming to washing | High | 0% | Not Started | Arsalan | 2026-06-29 19:00
168 | Washing | Mechanical | pressure gauge to install on rinse recycle loop pipes | High | 100% | Completed | Arsalan | 2026-06-29 19:00
169 | Washing | Mechanical | contamination/ fumes collector to be checked and installed on top | High | 0% | Not Started | Arsalan | 2026-06-29 19:00
170 | Washing | Mechanical | to install Pvc & wire brush on washing chain at top | High | 50% | Not Started | Arsalan | 2026-06-29 19:00
171 | Washing | Mechanical | Spray and Drying section's windows to be installed | High | 80% | Not Started | Arsalan | 2026-06-29 19:00
172 | Washing | Mechanical | Rinsing Recycling Tank — recoating & cleaning | High | 50% | In Progress | Saqib | 2026-06-29 19:00
173 | Washing | Mechanical | Spraying Jets Section — cleaning / scraping | High | 50% | In Progress | Saqib | 2026-06-29 19:00
174 | Washing | Electrical | Heaters to be Replaced | High | 80% | In Progress | Arsalan | 2026-06-29 19:00
175 | Washing | Mechanical | All gears greasing | High | 100% | Completed | Arsalan | 2026-06-29 19:00
176 | Washing | Mechanical | Gears alignment | High | 100% | Completed | Arsalan | 2026-06-29 19:00
177 | Washing | Mechanical | Separate storage tanks installation(detergent / cold / hot water) | High | 0% | Not Started | Saqib | 2026-06-29 19:00
178 | Press | Mechanical | main motor bearing change | High | 100% | Completed |  | 2026-07-07 19:00
179 | Lacquer | Mechanical | fumes motor winding to be done | High | 100% | Completed |  | 2026-07-06 19:00
180 | Lacquer | Mechanical | holders pin to be checked and repalced | Medium | 100% | Completed | Arsalan | 2026-07-06 19:00
181 | Lacquer Oven | Mechanical | oven heater to be checked | Medium | 100% | Completed |  | 2026-06-01 19:00

## HOW TO UPDATE (hidden)
HOW TO UPDATE — QUICK GUIDE
COLUMN / STEP | INSTRUCTION
COLUMN | WHAT TO DO | Arsalan
Machine | Click the cell — a dropdown appears. Pick the machine name. | Saqib
Category | Pick Electrical or Mechanical from the dropdown.
Task Description | Type the task clearly and briefly.
Priority | High = urgent / blocking. Medium = important. Low = when possible.
Progress | Type a number: 0 = not started, 50 = halfway done, 100 = complete.
Status | Pick from dropdown: Not Started / In Progress / Completed / Blocked / Pending Procurement.
Remarks | Short notes — vendor, reason for delay, Khalid sb instruction, etc.
Updated | Type today's date when you update any row.
Add a new task | Scroll to the bottom. Type in the next empty row. All dropdowns work there too.
Filter by machine | Click the filter arrow (▼) on the Machine column. Tick only the machine you want.
Hide completed | Click the filter arrow on Status. Untick Completed. Click OK.
Dashboard links | On the Dashboard, click any machine name (underlined blue) to jump straight to it.
Back to Dashboard | In the Tracker, click '← Dashboard' in the top-right corner of the sheet.