## TRACKER
AEROSOL PLANT · INSTALLATION TRACKER | [8 empty] | ← Dashboard
# | Machine | Category | Task Description | Priority | Progress | Status | Responsible | Remarks | Updated
1 | Accumulator | Electrical | Dry run | High | 0% | Not Started | Arsalan | on machine testing
2 | Accumulator | Mechanical | chain & bearing greasing | Medium | 50% | In Progress | Arsalan
3 | Auto strapping machine | Mechanical | to place and install at designated location | Medium | 0% | Not Started | Arsalan
4 | Auto strapping machine | Mechanical | Dry run | Low | 0% | Not Started | Arsalan
5 | Auto strapping machine | Electrical | wiring and connections to be done | Medium | 0% | Not Started | Arsalan
6 | Lacquer | Electrical | All heaters — check, fix or replace faulty | High | 100% | Completed | Arsalan | 2026-05-15
7 | Press | Mechanical | Press & Trimming compressor temporary line fixed | High | 100% | Completed | Arsalan | 2026-05-16
8 | Lacquer | Electrical | Blower main motor connection and testing | High | 100% | Completed | Arsalan | 2026-06-10
9 | Lacquer | Mechanical | Spray Guns — cleaned with thinner | High | 100% | Completed | Arsalan | 2026-06-10
10 | Lacquer | Mechanical | Spray Mount Drum — scraped & cleaned | High | 100% | Completed | Arsalan | 2026-06-10
11 | Lacquer | Mechanical | Mandrel Plate — scraped & cleaned | Medium | 100% | Completed | Saqib | 2026-06-10
12 | Lacquer | Mechanical | Exhaust Sieve — cleaned | Medium | 100% | Completed | Saqib | 2026-06-10
13 | Lacquer | Mechanical | Frame Body — cleaned | Medium | 100% | Completed | Saqib | 2026-06-10
14 | Lacquer | Mechanical | Oven Chain cleaning | Medium | 100% | Completed | Saqib | 2026-06-10
15 | Washing | Mechanical | chain installation | High | 90% | Not Started | Arsalan | 2026-06-11
16 | Compressor | Electrical | Compressor dryer and auto drain electrical connection | High | 50% | In Progress | Arsalan
17 | Compressor | Mechanical | Compressor piping — dryer and auto drain system | High | 95% | In Progress | Arsalan
18 | Compressor | Mechanical | main pipe to be elevated downward for smooth drainage | Medium | 0% | Not Started | Arsalan
19 | Compressor | Mechanical | individual section pipes/ branches to be supported/fixed/welded | Medium | 0% | Not Started | Arsalan
20 | Compressor | Electrical | dryer wiring and connection to be done. | High | 0% | Not Started | Arsalan
21 | decoration Oven | Electrical | Heaters to be checked and replaced if required | High | 0% | Not Started | Arsalan | sample needed for ordering
22 | decoration Oven | Electrical | Blower motor connection and testing | High | 100% | Completed | Arsalan
23 | decoration Oven | Electrical | temperature gauges to be checked & installed | High | 0% | Not Started | Arsalan
24 | decoration Oven | General | Lacquer Oven Dry run | High | 100% | Completed | Arsalan | Cleaning in progress & Heater testing in progress
25 | decoration Oven | Mechanical | Motors alignment w.r.t marking | High | 100% | Completed | Arsalan | Khalid Shb observations
26 | FG Conveyor | Mechanical | Realignment of conveyor to be done as per Lindsay recommendation | Medium | 0% | Not Started | Arsalan
27 | FG Conveyor | Electrical | connection/wiring to be done | Medium | 0% | Not Started | Arsalan
28 | General | General | Machine Operating Manuals | Medium | 10% | In Progress | Saqib
29 | General | General | Overall machine paint | Medium | 0% | Not Started | Saqib
30 | General | Mechanical | Modify exhaust duct pipes — prevent rainwater entry bends installation | Medium | 100% | Completed | Saqib
31 | General | Mechanical | Test each machine individually without load | Medium | 50% | In Progress | Arsalan
32 | General | General | Ensure proper cleaning of entire machine | Medium | 0% | Not Started | Saqib
33 | General | Mechanical | Scoop required for slug handling | Medium | 0% | Not Started | Saqib
34 | General | Mechanical | Baling machine procurement | Medium | 0% | Not Started | Saqib
35 | General | Mechanical | scrap collector container to be made/procured for trimming | Medium | 0% | Not Started | Saqib
36 | General | Electrical | White LED lighting for printing and oven area | Medium | 0% | Not Started | Saqib
37 | General | General | Make stands for all spare rolls | Medium | 0% | Not Started | Saqib
38 | General | General | Full operator toolset & tool trolley system | Medium | 0% | Not Started | Saqib
39 | General | General | Lab equipment to be sourced | Medium | 0% | Not Started | Saqib
40 | General | General | Dust bins for office areas | Medium | 0% | Not Started | Saqib
41 | General | General | Big cartons for temporary storage of cans | Medium | 0% | Not Started | Saqib
42 | General | General | Boxes / Bins for cans packing (Alpha Container) | Medium | 0% | Not Started | Saqib
43 | General | Electrical | Transformer load increase to 625 kW — utility application | High | 0% | Not Started | Saqib | Application in process
44 | General | Electrical | Ensure all exhaust fans on floor are operational | High | 70% | In Progress | Saqib | partially operational
45 | General | Mechanical | Operator's Platform | Medium | 0% | Not Started | Saqib | new to be ordered
46 | Lacquer | General | Internal Lacquering Dry run | High | 0% | Not Started | Arsalan | 2026-06-15
47 | Lacquer | Mechanical | lacquer Storage vessel installation with pneumatic fittings | Medium | 0% | Not Started | Saqib | 2026-06-15
48 | Lacquer | Mechanical | fixing can holders after cleaning | Medium | 0% | Not Started | Arsalan | 2026-06-15
49 | Lacquer | Mechanical | Cans Holders — dismantled, clean with thinner | Medium | 50% | In Progress | Saqib | 2026-06-15
50 | Lacquer | Mechanical | Small dedicated air tank / receiver for lacquer | Medium | 0% | Not Started | Saqib | 2026-06-15
51 | Lacquer oven | Mechanical | Oven Chain & bearing greasing | Medium | 50% | In Progress | Arsalan | 2026-06-15
52 | Lacquer oven | Electrical | closure of electrical panels | Medium | 0% | Not Started | Arsalan | 2026-06-15
53 | Lacquer oven | Mechanical | Oven back metallic cover sheet to place | Medium | 0% | Not Started | Arsalan | 2026-06-15
54 | Over Varnish | Mechanical | Rollers — dismantled, to be chrome plated | High | 100% | Completed | Saqib | 2026-06-15
55 | Printing | Mechanical | Rollers — dismantled, to be chrome plated | High | 80% | In Progress | Saqib | 2026-06-15
56 | Printing | Mechanical | Printing machine rollers — deep clean, rubber & chrome inspection | High | 80% | In Progress | Saqib | 2026-06-15
57 | Printing | Mechanical | All printing rollers — dismantle, clean, buff, chrome plate | High | 80% | In Progress | Saqib | 2026-06-15
58 | Printing | Electrical | CTC cleaning of machine panels interface | High | 80% | In Progress | Arsalan | 2026-06-15
#REF! | Washing | Mechanical | Heat exchanger for washing system — procure & install | High | 0% | Not Started | Saqib | 2026-06-15
#REF! | Washing | Mechanical | Inspect all rubber pipes — replace if damaged | High | 0% | Not Started | Arsalan | 2026-06-15
#REF! | Manual Strapping Machine | Mechanical | to place and install at designated location | Low | 0% | Not Started | Arsalan
#REF! | Manual Strapping Machine | Electrical | wiring and connections to be done | Low | 0% | Not Started | Arsalan
#REF! | Necking | Mechanical | Infeed tray installation from feeding unit to necking machine | Medium | 0% | Not Started | Arsalan
#REF! | Necking | Mechanical | PVC ejection pipe installation from necking for cans discharge | Medium | 0% | Not Started | Arsalan
#REF! | Necking | Mechanical | scrap collection tank to install from necking | Medium | 0% | Not Started | Arsalan
#REF! | Necking | Mechanical | Conveyor installation after ejection pipe | Medium | 0% | Not Started | Arsalan
#REF! | Necking | General | Necking machine Dry run | High | 50% | In Progress | Arsalan
#REF! | Necking | Electrical | Electrical troubleshooting and testing | High | 100% | Completed | Arsalan
#REF! | Necking | Mechanical | Cans Grippers / Holders — cleaning | Medium | 100% | Completed | Saqib
#REF! | Necking | Mechanical | Buffing and polishing on necking machine tools | Medium | 100% | Completed | Saqib
#REF! | Necking | Mechanical | Two sets of press dies, springs & nut bolts required | High | 0% | Not Started | Saqib
#REF! | Necking | Mechanical | Kluber oil & grease for necking machine | Medium | 0% | Not Started | Saqib
#REF! | Necking | Electrical | Necking machine — electrical supply troubleshooting for dry run | High | 20% | In Progress | Arsalan | Interlocking will be redesigned and checked
#REF! | Washing | Mechanical | Washing unit tanks — sizes and quantities for quotation | Medium | 0% | Not Started | Saqib | 2026-06-15
#REF! | Press | Electrical | Close all electrical panels and cable trays | High | 10% | In Progress | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Damping rubber pads over slug feeding tray | Low | 0% | Pending Procurement | Saqib | 2026-06-16
#REF! | Press | Mechanical | Gear Oil Lubrication pumping system setup | High | 0% | Not Started | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Slug Feeding Hopper sheet to be fixed | High | 80% | Completed | Saqib | 2026-06-16
#REF! | Press | Mechanical | Tools for press machine | High | 80% | Completed | Saqib | 2026-06-16
#REF! | Press | Electrical | Dust Collection blower installation | Medium | 0% | In Progress | Saqib | 2026-06-16
#REF! | Press | Electrical | SOV pneumatic press clutch service | High | 80% | Completed | Arsalan | 2026-06-16
#REF! | Press | Electrical | Hopper motor installation and testing | High | 100% | Completed | Arsalan | 2026-06-16
#REF! | Press | Electrical | Cable trays installation | High | 100% | Completed | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Press Clutch NRV repaired | High | 100% | Completed | Arsalan | 2026-06-16
#REF! | Overall Machine operation | Electrical | Main Power Cable Termination & Execution Plan | High | 0% | Not Started | Arsalan | 2026-06-13
#REF! | Overall Machine operation | Electrical | Main Power Cable procurement | High | 0% | Pending Procurement | Saqib | Quotation awaiting for execution
#REF! | Overall Machine operation | Electrical | Electrical panels for power distribution | High | 0% | Pending Procurement | Arsalan | Quotation awaiting for execution
#REF! | Overall Machine operation | Electrical | Verify electrical panels, wiring & interlocks — Press to Washing | High | 50% | In Progress | Arsalan | Till Washing Machine electrical Work is completed
#REF! | Overall Machine operation | Electrical | Testing of Control Logics & Circuits | High | 0% | Not Started | Arsalan
#REF! | Overall Machine operation | Electrical | Verify electrical panels, wiring & interlocks — Washing to Necking | High | 50% | In Progress | Arsalan
#REF! | Press | Mechanical | Press timing and alignment with testing | High | 100% | Completed | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Die & punch stroke setting | High | 100% | Completed | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Slug tray on/of switch to be installed | High | 0% | Not Started | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Dust Collection blower piping | Medium | 0% | Pending Procurement | Saqib | 2026-06-16
#REF! | Press | Mechanical | Welding & fixing gear oil tank brackets and sheet | Medium | 40% | In Progress | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Fixing the lubrication tray properly with a slope for drainage | Medium | 0% | Not Started | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Place and install the Oil collection tank directly under the tray | Medium | 0% | Not Started | Arsalan | 2026-06-16
#REF! | Press | Mechanical | Installation of Level sensor and Filter on the oil tank | Medium | 0% | Not Started | Arsalan | 2026-06-16
#REF! | Trimming | Mechanical | Installation of piping of Trimming Of blower | High | 0% | In Progress | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Conveyor alignment — Trimming to Washing | High | 50% | In Progress | Arsalan | 2026-06-19
#REF! | Trimming | Electrical | Trimming Scrap collector wiring and troubleshooting | High | 0% | Not Started | Saqib | 2026-06-19
#REF! | Trimming | Electrical | Electrical Panel checked / Tested | High | 50% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Electrical | Startup main motor | High | 50% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Electrical | Pneumatic and Electrical operation check | High | 50% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Trimming startup | High | 80% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Conveyor — Press to Trimming input | High | 80% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Trimming machine dry run | High | 80% | Completed | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Install safety guard for suction at scrap generation point | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | closure of chain/gears/pneumatic assembly with box | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Electrical | closure of all cable trays/ panels | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | pneumatic pressure valve for ejector pressure to install | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Installation of trimming blower | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Fixing of Manual Oil Lubrication System | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Addition of closed cabinet for trim collection on machine side | High | 0% | Not Started | Arsalan | 2026-06-19
#REF! | Trimming | Mechanical | Oiling / greasing / parts replacement / testing | High | 80% | In Progress | Arsalan | 2026-06-19
#REF! | Washing | Electrical | Heaters to be checked and replaced if required | High | 0% | In Progress | Arsalan | 2026-06-19
#REF! | Base Coat | Mechanical | Fumes collector piping to install | Medium | 0% | Not Started | Saqib | 2026-06-20
#REF! | Over Varnish | Mechanical | Fumes collector piping to install | High | 0% | Not Started | Saqib | 2026-06-20
#REF! | Base Coat | Mechanical | Rollers Housing — cleaned and greased | Medium | 60% | In Progress | Saqib | 2026-06-25
#REF! | Base Coat | Mechanical | Mandrels — cleaned | Medium | 60% | In Progress | Saqib | 2026-06-25
#REF! | Base Coat | Mechanical | Frame Body — cleaned | Medium | 60% | In Progress | Saqib | 2026-06-25
#REF! | Base Coat | Mechanical | Spare Rubberize rollers | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Base Coat | Mechanical | Spare Rubberize rollers | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Base Coat | Mechanical | Air regulator pneumatic fitting to check and rectify and fixation | Medium | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Base Coat | Mechanical | driving gear chain box enclosure at back | Medium | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Base Coat | Electrical | closure of all cable trays/ panels | Medium | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Base Coat | Mechanical | Rawal bolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Over Varnish | Mechanical | Spare Rubberize rollers | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Over Varnish | Electrical | closure of all cable trays/ panels | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Over Varnish | Mechanical | Rawal bolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Over Varnish | Mechanical | varnish pump placement and installation with piping | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Over Varnish | General | Printing Oven Dry run | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Over Varnish | Electrical | Motors checking and troubleshooting | High | 50% | In Progress | Arsalan | 2026-06-25
#REF! | Over Varnish | Mechanical | Mandrels — cleaned | High | 80% | In Progress | Saqib | 2026-06-25
#REF! | Over Varnish | Mechanical | Rollers Housing — cleaned and greased | High | 80% | In Progress | Arsalan | 2026-06-25
#REF! | Over Varnish | Mechanical | Frame Body — cleaned | High | 80% | In Progress | Arsalan | 2026-06-25
#REF! | Base Coat | Electrical | PLC installation & termination | High | 15% | In Progress | Arsalan | 2026-06-25
#REF! | Over Varnish | Electrical | PLC installation & termination | High | 15% | In Progress | Arsalan | 2026-06-25
#REF! | Printing | Electrical | PLC installation & termination | High | 15% | In Progress | Arsalan | 2026-06-25
#REF! | Printing | Mechanical | Bearings — cleaning & greasing | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Printing | Mechanical | Ink Fountain — cleaning | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Printing | Mechanical | Roller Train Frame — cleaning | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Printing | Mechanical | Dismantle all rollers for inspection & Cleaning | High | 50% | In Progress | Saqib | 2026-06-25
#REF! | Tumbler | Electrical | Mixer installation and automation — auto feeding flow design | Medium | 0% | Pending Procurement | Arsalan | quotation awaiting for conveyor from Arsalan & Lindsay
#REF! | Tumbler | General | Slug Mixing Unit Dry run | Medium | 100% | Completed | Arsalan | Working on its auto feeding system
#REF! | Tumbler | Mechanical | Tumbler/Mixer wiring and connections to be done | High | 0% | Not Started | Arsalan
#REF! | Tumbler | Electrical | Main motor testing | High | 100% | Completed | Arsalan
#REF! | Tumbler | Mechanical | Tumbler/Mixer installation on platform | High | 50% | In Progress | Arsalan
#REF! | Printing | Electrical | Servo motor troubleshooting | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Printing | Mechanical | Aluminum oil tank — fabricate & install | High | 0% | Not Started | Saqib | 2026-06-25
#REF! | Printing | Electrical | closure of all cable trays/ panels | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Printing | Mechanical | Rawlbolts anchoring to be done on the foundation | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Printing | General | Printing Machine Dry run | High | 0% | Not Started | Arsalan | 2026-06-25
#REF! | Washing | Mechanical | Washing machine piping and blower installation | High | 20% | In Progress | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Washing unit drain flexible pipes after tank installation | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Washing Machine Dry run | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Electrical | Electrical Operating control panel to be relocated from trimming to washing | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | pressure gauge to install on rinse recycle loop pipes | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | contamination/ fumes collector to be checked and installed on top | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | to install Pvc & wire brush on washing chain at top | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Spray and Drying section's windows to be installed | High | 0% | Not Started | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Rinsing Recycling Tank — recoating & cleaning | High | 50% | In Progress | Saqib | 2026-06-30
#REF! | Washing | Mechanical | Spraying Jets Section — cleaning / scraping | High | 50% | In Progress | Saqib | 2026-06-30
#REF! | Washing | Electrical | Heaters to be Replaced | High | 0% | Pending Procurement | Saqib | 2026-06-30
#REF! | Washing | Mechanical | All gears greasing | High | 50% | Completed | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Gears alignment | High | 50% | Completed | Arsalan | 2026-06-30
#REF! | Washing | Mechanical | Separate storage tanks installation(detergent / cold / hot water) | High | 0% | Not Started | Saqib | 2026-06-30
i
`